## Recording Sheet
ID | Test Case/Script | Test Objective (if more than one) | Test Step Header | Defect Description | Date Identified | Identified By | Criticality | Defect Status | Analysis / Resolution Comments | Test Comments | JIRA Board Reference
1 | https://github.com/alex-kalinka-cruk/fgc_crispr_pipeline_UAT/blob/master/analysis/UAT-analysis.Rmd | Transformation of data from FTP S3 bucket to REL input bucket | Manual test of data transformation for multi-SLX use case. | Original multi-SLX data not copied from 'ftps-core-ftps3bucket-1b6k14wlq0yu7' to 'transformed-data-bucket-rel' (e.g. 'SLX-100.s_1.SRR8983578.fastq.gz'). Possibly because the filenames are not as expected - need clarification. | 2020-02-11 | ATK | Major | Identified
2 | https://github.com/alex-kalinka-cruk/fgc_crispr_pipeline_UAT/blob/master/analysis/UAT-analysis.Rmd | Testing concordance of v1 and v2 output | # Concordance of pipeline outputs with v1 | The order of the columns (sample names) in the 'combined_counts.txt' file seems to depend on the order of samples in the original json analysis config file even though the data is identical. | 2020-02-11 | ATK | Trivial | Closed
3 | https://github.com/alex-kalinka-cruk/fgc_crispr_pipeline_UAT/blob/master/analysis/UAT-analysis.Rmd | Testing concordance of v1 and v2 output | # Concordance of pipeline outputs with v2 | The order of the sgRNAs in the 'combined_counts.txt' file also seems to depend on the order of the samples in the original json file (perhaps ordering of rows occurs across sample column order). | 2020-02-11 | ATK | Trivial | Closed
4 | https://github.com/alex-kalinka-cruk/fgc_crispr_pipeline_UAT/blob/master/analysis/UAT-analysis.Rmd | Testing concordance of v1 and v2 output | # Concordance of pipeline outputs with v3 | The 'neg.rank' and 'pos.rank' columns are not identical in the Mageck output - there seems to be some randomness in the ranking of tied genes. This also impacts the order of the genes in the output file. | 2020-02-11 | ATK | Trivial | Closed
5 | https://github.com/alex-kalinka-cruk/fgc_crispr_pipeline_UAT/blob/master/analysis/UAT-analysis.Rmd | Testing concordance of v1 and v2 output | # Concordance of pipeline outputs with v4 | "GeneConnectivity" interpretation output is private to AZ | 2020-02-11 | ATK | Trivial | Closed
6 | https://github.com/alex-kalinka-cruk/fgc_crispr_pipeline_UAT/blob/master/analysis/UAT-analysis.Rmd | Testing concordance of v1 and v2 output | # Concordance of pipeline outputs with v5 | "PathwayAnalysis" interpretation output is private to v2. | 2020-02-11 | ATK | Trivial | Closed
7 | https://github.com/alex-kalinka-cruk/fgc_crispr_pipeline_UAT/blob/master/analysis/UAT-analysis.Rmd | Testing concordance of v1 and v2 output | # Concordance of pipeline outputs with v6 | "fastq" and "fastqc" sub-folders no longer saved in v2 'crisprn' sub-folder, but at the same level as 'crisprn' folder. | 2020-02-11 | ATK | Trivial | Closed
8 | https://github.com/alex-kalinka-cruk/fgc_crispr_pipeline_UAT/blob/master/analysis/UAT-analysis.Rmd | Testing concordance of v1 and v2 output | # Concordance of pipeline outputs with v7 | "counts' sub-folder within "crisprn" folder now contains the merging counts log, for v1 it contained the log for individual sample counts as well as the merging counts log. | 2020-02-11 | ATK | Trivial | Closed

## Picklists
Critical | Identified
Major | Prioritised
Minor | Analysed
Trivial | Resolved
Verified
Closed